## Gantt Chart
	[Open-Source CEM and Additive Manufacturing, Year 1]				13%
	[Whittier College]
	[Profs. J. Hanson, F. Park, S. Zorba, S. Lagan, G. Piner]		Monday, June 19, 2023
	[Nayeli Camacho, Shaun Dunnick]

WBS	Task Names	Responsible Colleagues	Start	Net Work Days	Finish	% Complete	Net Work Days	Days Completed	Days Remaining	Days to Deadline		Jul 2024	Aug 2024	Sept 2024	Oct 2024	Nov 2024	Dec 2024	Jan 2025	Feb 2025	Mar 2025	Apr 2025	May 2025	Jun 2025	Jul 2025	Aug 2025
			01-Jul-2024	300	23-Aug-2025	13%	300	40	260	796
	Hardware Acquisition (Weight=10%)	[Prof. Hanson, N. Camacho, F. Park]	01-Jul-2024	34	15-Aug-2024	100%	34	34	0	423
	3D Printer Acquisition
	Obtain quotes	[Prof. Hanson]	01-Jul-2024	6	08-Jul-2024	100%	6	6	0	385
	Complete purchase	[N. Camacho]	10-Jul-2024	4	15-Jul-2024	100%	4	4	0	392
	3D Printer Filament Acquisition
	Obtain quotes	[Prof. Hanson]	01-Jul-2024	6	08-Jul-2024	100%	6	6	0	385
	Complete purchase	[N. Camacho]	10-Jul-2024	4	15-Jul-2024	100%	4	4	0	392
	GPU/Multicore Server
	Perform market comparison	[F. Park]	01-Jul-2024	24	01-Aug-2024	100%	24	24	0	409
	Obtain quotes	[Prof. Hanson]	01-Aug-2024	10	14-Aug-2024	100%	10	10	0	422
	Complete purchase	[N. Camacho]	14-Aug-2024	2	15-Aug-2024	100%	2	2	0	423
	RF Lab Hardware
	RF cables and connectors	[Prof. Hanson]	01-Jul-2024	24	01-Aug-2024	100%	24	24	0	409

	Recruitment (Weight=5%)	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	0%	22	0	22	462
	Standard undergraduate recruitment procedure
	Undergraduate STEM researchers	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	0%	22	0	22	462
	Undergraduate app/code designers	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	0%	22	0	22	462

	Run Published CEM Codes (Weight=5%)	[Prof. Hanson, Undergraduates 1,2]	23-Sep-2024	12	08-Oct-2024	0%	12	0	12	477
	Initial CEM Training, Linux Accts.
	CEM Training	[Prof. Hanson, Undergraduates 1,2]	23-Sep-2024	6	30-Sep-2024	0%	6	0	6	469
	Account creation	[Prof. Hanson]	23-Sep-2024	6	30-Sep-2024	0%	6	0	6	469
	Updating CEM Code
	Unpack and test original code	[Prof. Hanson]	23-Sep-2024	12	08-Oct-2024	0%	12	0	12	477

	Course Integrations (Weight=10%)	[Profs. Hanson, Lagan, Zorba, Piner, and Park]	01-Jul-2024	300	23-Aug-2025	0%	300	0	300	796
	Physics Courses
	Algebra-Based Physics II	[Prof. Hanson]	01-Jul-2024	11	15-Jul-2024	0%	11	0	11	392
	Calculus-Based Physics II	[Prof. Hanson]	01-Jul-2024	11	15-Jul-2024	0%	11	0	11	392
	Optics	[Profs. Zorba and Hanson]	15-Dec-2024	23	15-Jan-2025	0%	23	0	23	576
	Electromagnetic Theory	[Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	0%	40	0	40	431
	Computational Physics	[Profs. Lagan and Hanson]	15-Dec-2024	23	15-Jan-2025	0%	23	0	23	576
	Computer Science Courses
	Computer Logic and Digital Circuit Design	[Prof. Hanson]	15-May-2025	72	23-Aug-2025	0%	72	0	72	796
	Digital Signal Processing	[Prof. Hanson]	01-Aug-2025	16	23-Aug-2025	0%	16	0	16	796
	Introduction to Data Science with Python	[Profs. Hanson and Piner]	01-Jul-2024	40	23-Aug-2024	0%	40	0	40	431
	Machine Learning	[Profs. Hanson and Park]	15-Jan-2025	87	15-May-2025	0%	87	0	87	696

	Primary CEM Research, Semesters 1, 2 (Weight=10%)	[Prof. Hanson, Undergraduates 1,2]	23-Aug-2024	190	15-May-2025	34%	190	63	127	696
	CEM Simulations, Data Visualization
	3D visualization of RF horn design	[Prof. Hanson, Undergraduate 1]	23-Sep-2024	7	01-Oct-2024	100%	7	7	0	470
	Time-domain computations, phase analysis	[Prof. Hanson, Undergraduate 1]	01-Oct-2024	24	01-Nov-2024	100%	24	24	0	501
	S-Parameters analysis	[Prof. Hanson, Undergraduate 1]	01-Oct-2024	24	01-Nov-2024	75%	24	18	6	501
	Inclusion of coaxial cable in simulation	[Prof. Hanson, Undergraduate 1]	01-Nov-2024	31	15-Dec-2024	15%	31	4	27	545
	Machine Learning Optimization
	Background research for algorithms	[Prof. Hanson, Undergraduate 2]	23-Sep-2024	30	01-Nov-2024	100%	30	30	0	501
	Learning genetic programming styles	[Prof. Hanson, Undergraduate 2]	23-Sep-2024	30	01-Nov-2024	25%	30	7	23	501
	CEM implementation with basic RF horn	[Prof. Hanson, Undergraduate 2]	01-Nov-2024	54	15-Jan-2025	10%	54	5	49	576
	RF antenna optimization	[Prof. Hanson, Undergraduate 2]	15-Jan-2025	87	15-May-2025	0%	87	0	87	696

	Additive Manufacturing, Semesters 1, 2 (Weight=10%)	[S. Dunnick, Prof. Hanson, Undergraduate 3]	01-Jul-2024	229	15-May-2025	0%	229	0	229	696
	Printing with PLA Filament
	Updating prior designs	[S. Dunnick, Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	0%	40	0	40	431
	Practice file format conversion	[S. Dunnick, Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	0%	40	0	40	431
	Print test object	[S. Dunnick, Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	0%	40	0	40	431
	Print PLA antenna model	[S. Dunnick, Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	0%	40	0	40	431
	Printing with Electrifi Filament
	Print test object	[S. Dunnick, Undergraduate 3]	23-Sep-2024	17	15-Oct-2024	0%	17	0	17	484
	Perform resistivity measurements	[S. Dunnick, Undergraduate 3]	15-Oct-2024	14	01-Nov-2024	0%	14	0	14	501
	Print simple antenna	[S. Dunnick, Undergraduate 3]	01-Nov-2024	31	15-Dec-2024	0%	31	0	31	545
	Print complex antenna	[S. Dunnick, Undergraduate 3]	15-Dec-2024	109	15-May-2025	0%	109	0	109	696

	Application Development, Semesters 1, 2 (Weight=10%)	[Prof. Hanson, Undergraduate 4]	23-Aug-2024	190	15-May-2025	0%	190	0	190	696
	Creating Project Plan with Students
	Creating kanban taskflow	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	0%	22	0	22	462
	Updating prior code	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	0%	22	0	22	462
	Experimenting with Android SDK	[Undergraduate 4]	23-Sep-2024	60	15-Dec-2024	0%	60	0	60	545
	Designing Visual Environment
	Updating prior designs	[Undergraduate 4]	15-Dec-2024	109	15-May-2025	0%	109	0	109	696
	Displaying content on Android app	[Undergraduate 4]	01-Feb-2025	74	15-May-2025	0%	74	0	74	696

	Primary CEM Research, Summer 2025 (Weight=20%)	[Prof. Hanson, Undergraduates 1,2]	15-May-2025	72	23-Aug-2025	0%	72	0	72	796
	CEM Simulations, Data Visualization
	3D visualization of optimized antenna	[Prof. Hanson, Undergraduate 1]	15-May-2025	12	01-Jun-2025	0%	12	0	12	713
	S-Parameters in complex media	[Prof. Hanson, Undergraduate 1]	01-Jun-2025	10	15-Jun-2025	0%	10	0	10	727
	CEM for 3D arrays in complex media	[Prof. Hanson, Undergraduate 1]	15-Jun-2025	50	23-Aug-2025	0%	50	0	50	796
	RX/TX with phased arrays in complex media	[Prof. Hanson, Undergraduate 1]	15-Jun-2025	50	23-Aug-2025	0%	50	0	50	796
	Machine Learning Optimization
	3D visualization of optimized antenna	[Prof. Hanson, Undergraduate 2]	15-May-2025	12	01-Jun-2025	0%	12	0	12	713
	Explore HPol array optimizations in ice	[Prof. Hanson, Undergraduate 2]	01-Jun-2025	60	23-Aug-2025	0%	60	0	60	796

	Additive Manufacturing, Summer 2025 (Weight=20%)	[S. Dunnick, Undergraduates 1,3]	15-May-2025	72	23-Aug-2025	0%	72	0	72	796
	Printing with Electrifi Filament
	Updating prior designs	[S. Dunnick, Undergraduate 3]	15-May-2025	34	01-Jul-2025	0%	34	0	34	743
	Continue printing complex antenna	[S. Dunnick, Undergraduate 3]	15-May-2025	34	01-Jul-2025	0%	34	0	34	743
	Real S-parameter measurement	[Prof. Hanson, Undergraduate 3]	01-Jul-2025	39	23-Aug-2025	0%	39	0	39	796
	Real radiation pattern measurement	[Prof. Hanson, Undergraduate 3]	01-Jul-2025	39	23-Aug-2025	0%	39	0	39	796

## Sheet2
	[Open-Source CEM and Additive Manufacturing, Year 2]				0%
	[Whittier College]
	[Prof. J. Hanson]		Monday, June 19, 2023
	[Nayeli Camacho, Shaun Dunnick]

WBS	Task Names	Responsible Colleagues	Start	Net Work Days	Finish	% Complete	Net Work Days	Days Completed	Days Remaining	Days to Deadline		Jul 2025	Aug 2025	Sept 2025	Oct 2026	Nov 2025	Dec 2025	Jan 2026	Feb 2026	Mar 2026	Apr 2026	May 2026	Jun 2026	Jul 2026	Aug 2026
			01-Jul-2025	299	23-Aug-2026	0%	299	0	299	1161
	Hardware Acquisition (Weight=5%)	[Prof. Hanson, N. Camacho]	01-Jul-2025	39	23-Aug-2025	0%	39	0	39	796
	RF lab hardware
	RF phase shifters	[Prof. Hanson]	01-Jul-2025	11	15-Jul-2025	0%	11	0	11	757
	Tektronix MDO with >1GHz BW, 4-channel	[Prof. Hanson]	15-Jul-2025	14	01-Aug-2025	0%	14	0	14	774
	Obtain quotes, develop purchase orders	[N. Camacho]	01-Aug-2025	11	15-Aug-2025	0%	11	0	11	788
	Complete purchases	[N. Camacho]	15-Aug-2025	6	23-Aug-2025	0%	6	0	6	796

	Recruitment (Weight=5%)	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	0%	22	0	22	827
	Standard undergraduate recruitment procedure
	Undergraduate STEM researchers	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	0%	22	0	22	827
	Undergraduate app/code designers	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	0%	22	0	22	827
	Undergraduate Spanish translator	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	0%	22	0	22	827

	Primary CEM Research, Semester 3 (Weight=15%)	[Prof. Hanson, Undergraduates 1,2]	23-Sep-2025	60	15-Dec-2025	0%	60	0	60	910
	CEM application to UHE neutrino research
	Explore horizontal array polarization in ice	[Prof. Hanson, Undergraduate 1]	23-Sep-2025	29	01-Nov-2025	0%	29	0	29	866
	Polarization response calculation	[Prof. Hanson, Undergraduate 1]	01-Nov-2025	31	15-Dec-2025	0%	31	0	31	910
	S-Parameters in complex media	[Prof. Hanson, Undergraduate 1]	01-Nov-2025	31	15-Dec-2025	0%	31	0	31	910
	Machine Learning Optimization
	Search for HPol array optimization with machine learning	[Prof. Hanson, Undergraduate 2]	23-Sep-2025	29	01-Nov-2025	0%	29	0	29	866
	Adjusting genetic programming and testing new algorithms	[Prof. Hanson, Undergraduate 2]	01-Nov-2025	31	15-Dec-2025	0%	31	0	31	910

	Additive Manufacturing, Semesters 3,4 (Weight=15%)	[S. Dunnick, Undergraduate 3]	23-Aug-2025	190	15-May-2026	0%	190	0	190	1061
	Printing with Electrifi filament
	Continue print progress from Summer 2025	[S. Dunnick, Undergraduate 3]	23-Sep-2025	29	01-Nov-2025	0%	29	0	29	866
	Modify designs to accommodate Hpol results	[S. Dunnick, Undergraduate 3]	01-Nov-2025	31	15-Dec-2025	0%	31	0	31	910
	Begin array printing and integration	[S. Dunnick, Undergraduate 3]	15-Dec-2025	110	15-May-2026	0%	110	0	110	1061
	RF bench testing of prototype array	[S. Dunnick, Undergraduate 3]	15-Jan-2026	87	15-May-2026	0%	87	0	87	1061

	Application Development., Semesters 3,4 (Weight=20%)	[Prof. Hanson, Undergraduate 4, Translator]	23-Aug-2025	190	15-May-2026	0%	190	0	190	1061
	Creating project plan with students
	Update Kanban taskflow	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	0%	22	0	22	827
	Implementation in Android SDK, bilingual translation	[Undergraduate 4, Translator]	23-Aug-2025	81	15-Dec-2025	0%	81	0	81	910
	Designing visual environment
	Integrating visual content on Android app	[Undergraduate 4, Translator]	15-Jan-2026	87	15-May-2026	0%	87	0	87	1061
	Experimenting with machine learning integration	[Undergraduate 4]	15-Jan-2026	87	15-May-2026	0%	87	0	87	1061

	Publication in Electronics, Semester 4 (Weight=20%)	[Prof. Hanson, Undergraduates 1,2,3, N. Camacho]	15-Jan-2026	157	23-Aug-2026	0%	157	0	157	1161
	Compiling results, writing the article
	Creating outline, writing text, gathering references	[Prof. Hanson]	15-Jan-2026	87	15-May-2026	0%	87	0	87	1061
	Gathering results and polishing figures	[Undergraduates 1,2,3]	15-Jan-2026	87	15-May-2026	0%	87	0	87	1061
	Publishing
	Corresponding with referees and editor	[Prof. Hanson]	15-May-2026	34	01-Jul-2026	0%	34	0	34	1108
	Copy editing, paying journal fees	[Prof. Hanson, M. Camacho]	01-Jul-2026	38	23-Aug-2026	0%	38	0	38	1161

	CEM/3D Print Summer Research 2026 (Weight=20%)	[Prof. Hanson, S. Dunnick, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	71	0	71	1161
	Finish backlog of prior work
	Publication, HPol analysis, machine learning optimizations	[Prof. Hanson, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	71	0	71	1161
	Prototype testing
	Practicing design loop: CEM to print	[Prof. Hanson, S. Dunnick, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	71	0	71	1161
	Integration of prototype array	[Prof. Hanson, S. Dunnick, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	71	0	71	1161
	Archiving progress
	Creating official, public code repository	[Prof. Hanson, Undergraduate 1]	01-Aug-2026	15	23-Aug-2026	0%	15	0	15	1161
	CAD design storage	[Prof. Hanson, Undergraduate 1]	01-Aug-2026	15	23-Aug-2026	0%	15	0	15	1161

## Sheet3
	[Open-Source CEM and Additive Manufacturing, Year 3]				0%
	[Whittier College]
	[Profs. J. Hanson, F. Park, S. Zorba, S. Lagan, G. Piner]		Monday, June 19, 2023
	[Nayeli Camacho, Shaun Dunnick]

WBS	Task Names	Responsible Colleagues	Start	Net Work Days	Finish	% Complete	Net Work Days	Days Completed	Days Remaining	Days to Deadline		Jul 2026	Aug 2026	Sept 2026	Oct 2026	Nov 2026	Dec 2026	Jan 2027	Feb 2027	Mar 2027	Apr 2027	May 2027	Jun 2027	Jul 2027	Aug 2027
			01-Jul-2026	299	23-Aug-2027	0%	299	0	299	1526
	Hardware Acquisition (Weight=5%)	[N. Camacho]	01-Jul-2026	61	23-Sep-2026	0%	61	0	61	1192
	Android mobile phones for testing
	Shop for best deals	[N. Camacho]	01-Jul-2026	6	08-Jul-2026	0%	6	0	6	1115
	Complete purchase	[N. Camacho]	08-Jul-2026	3	10-Jul-2026	0%	3	0	3	1117
	Restocking of 3D Printing Supply
	Electrifi filament	[N. Camacho]	10-Jul-2026	4	15-Jul-2026	0%	4	0	4	1122
	Prusa printers	[N. Camacho]	15-Jul-2026	13	01-Aug-2026	0%	13	0	13	1139

	Recruitment (Weight=5%)	[Prof. Hanson]	23-Aug-2026	23	23-Sep-2026	0%	23	0	23	1192
	Standard undergraduate recruitment procedure
	Undergraduate STEM researchers	[Prof. Hanson]	23-Aug-2026	23	23-Sep-2026	0%	23	0	23	1192
	Undergraduate app/code designers	[Prof. Hanson]	23-Aug-2026	23	23-Sep-2026	0%	23	0	23	1192

	Primary CEM Research, Semesters 5,6 (Weight=15%)	[Prof. Hanson, Undergraduates 1,2]	23-Sep-2026	168	15-May-2027	0%	168	0	168	1426
	CEM Application to CReSIS Research
	Modify antenna code to fit drone, 3D visualization	[Prof. Hanson, Undergraduate 1]	23-Sep-2026	50	01-Dec-2026	0%	50	0	50	1261
	S-parameters and radiation pattern	[Prof. Hanson, Undergraduate 1]	01-Dec-2026	11	15-Dec-2026	0%	11	0	11	1275
	Compute volume and weight	[Prof. Hanson, Undergraduate 1]	15-Dec-2026	24	15-Jan-2027	0%	24	0	24	1306
	Radio echo CEM and Open Polar Server data	[Prof. Hanson, Undergraduate 1]	15-Jan-2027	86	15-May-2027	0%	86	0	86	1426
	Machine Learning Optimization
	Utilize machine learning to optimize drone structure	[Prof. Hanson, Undergraduate 2]	23-Sep-2026	168	15-May-2027	0%	168	0	168	1426

	Additive Manufacturing, Semesters 5,6 (Weight=15%)	[S. Dunnick, Prof. Hanson, Undergraduate 3]	23-Sep-2026	168	15-May-2027	0%	168	0	168	1426
	Restart drone project
	Reverse engineer parts list	[Undergraduate 3]	23-Sep-2026	7	01-Oct-2026	0%	7	0	7	1200
	Learn to operate the old drone	[Undergraduate 3]	01-Oct-2026	22	01-Nov-2026	0%	22	0	22	1231
	Payload testing	[Undergraduate 3]	01-Nov-2026	22	01-Dec-2026	0%	22	0	22	1261
	Print new parts with PLA, lengthen arms	[S. Dunnick, Undergraduate 3]	01-Dec-2026	11	15-Dec-2026	0%	11	0	11	1275
	Printing with Electrifi Filament
	Print conductive parts for array integration	[S. Dunnick, Undergraduate 3]	15-Dec-2026	45	15-Feb-2027	0%	45	0	45	1337
	Perform resistivity measurements	[Undergraduate 3]	15-Feb-2027	11	01-Mar-2027	0%	11	0	11	1351
	RF bench testing of conductive parts	[Prof. Hanson, Undergraduate 3]	01-Mar-2027	24	01-Apr-2027	0%	24	0	24	1382
	Drone integration	[Prof. Hanson, Undergraduate 3]	01-Apr-2027	32	15-May-2027	0%	32	0	32	1426

	Application Development, Semesters 5,6 (Weight=20%)	[Phys. Dept., Undergraduate 4]	23-Sep-2026	202	01-Jul-2027	0%	202	0	202	1473
	Initial data collection with students
	Creating kanban taskflow	[Prof. Hanson]	23-Aug-2026	7	01-Sep-2026	0%	7	0	7	1170
	Install on multiple Android devices, debugging	[Prof. Hanson]	01-Sep-2026	23	01-Oct-2026	0%	23	0	23	1200
	Collect basic data sets	[Undergraduate 4]	01-Oct-2026	54	15-Dec-2026	0%	54	0	54	1275
	Designing Visual Environment
	Obtain feedback on visual feel	[Undergraduate 4]	01-Oct-2026	22	01-Nov-2026	0%	22	0	22	1231
	Modify visual elements	[Undergraduate 4]	01-Nov-2026	32	15-Dec-2026	0%	32	0	32	1275
	Begin Presentation of Initial Results
	Present initial results to department	[Profs. Hanson, Zorba, Piner, and Lagan]	15-Dec-2026	24	15-Jan-2027	0%	24	0	24	1306
	OER talk in Wardman Collaboratory	[Prof. Hanson, Undergraduate 4]	15-Jan-2027	22	15-Feb-2027	0%	22	0	22	1337
	Assemble rough draft for publication	[Prof. Hanson, Undergraduate 4]	15-Feb-2027	65	15-May-2027	0%	65	0	65	1426
	Collect Course-Level Data Set
	Implement in introductory physics course	[Prof. Hanson, Undergraduate 4]	15-Jan-2027	86	15-May-2027	0%	86	0	86	1426
	Perform on-going data analysis	[Prof. Hanson, Undergraduate 4]	15-May-2027	34	01-Jul-2027	0%	34	0	34	1473

	Application Development, Summer 2027 (Weight=20%)	[Prof. Hanson, Undergraduates 4,5]	15-May-2027	71	23-Aug-2027	0%	71	0	71	1526
	Preparing publication for American Journal of Physics
	Main data analysis and visualization	[Prof. Hanson, Undergraduate 4]	15-May-2027	12	01-Jun-2027	0%	12	0	12	1443
	Compare users vs. non-users	[Prof. Hanson, Undergraduate 4]	01-Jun-2027	11	15-Jun-2027	0%	11	0	11	1457
	Create outline and prepare abstract/text	[Prof. Hanson, Undergraduate 4]	15-Jun-2027	50	23-Aug-2027	0%	50	0	50	1526
	Machine learning and optimization
	Articulate and refine the structure for publication	[Prof. Hanson, Undergraduate 4]	15-May-2027	12	01-Jun-2027	0%	12	0	12	1443
	Train a new undergraduate operator for continuity	[Prof. Hanson, Undergraduate 5]	01-Jun-2027	60	23-Aug-2027	0%	60	0	60	1526

	Additive Manufacturing, Summer 2027 (Weight=20%)	[Prof. Hanson, S. Dunnick, Undergraduate 3]	15-May-2027	71	23-Aug-2027	0%	71	0	71	1526
	Drone integration
	Adding solar charging	[Prof. Hanson, Undergraduate 3]	15-May-2025	72	23-Aug-2025	0%	72	0	72	796
	Adding TX/RX capability	[Prof. Hanson, Undergraduate 3]	15-May-2025	72	23-Aug-2025	0%	72	0	72	796
	Begin collaboration with CReSIS personnel	[Prof. Hanson]	15-May-2025	72	23-Aug-2025	0%	72	0	72	796

## Sheet4
	[Open-Source CEM and Additive Manufacturing, Year 4]				0%
	[Whittier College]
	[Profs. J. Hanson, F. Park, S. Zorba, S. Lagan, G. Piner]		Monday, June 19, 2023
	[Nayeli Camacho, Shaun Dunnick]

WBS	Task Names	Responsible Colleagues	Start	Net Work Days	Finish	% Complete	Net Work Days	Days Completed	Days Remaining	Days to Deadline		Jul 2027	Aug 2027	Sept 2027	Oct 2027	Nov 2027	Dec 2027	Jan 2028	Feb 2028	Mar 2028	Apr 2028	May 2028	Jun 2028	Jul 2028	Aug 2028
			01-Jul-2027	300	23-Aug-2028	0%	300	0	300	1892
	Hardware Acquisition (Weight=5%)	[Prof. Hanson]	01-Jul-2027	11	15-Jul-2027	0%	11	0	11	1487
	Drone hardware acquisition
	Electronics/wiring	[Prof. Hanson]	01-Jul-2027	11	15-Jul-2027	0%	11	0	11	1487
	Structural components	[Prof. Hanson]	01-Jul-2027	11	15-Jul-2027	0%	11	0	11	1487
	Solar charging and batteries	[Prof. Hanson]	01-Jul-2027	11	15-Jul-2027	0%	11	0	11	1487
	Recruit the next student for drone project	[Prof. Hanson]	01-Jul-2027	11	15-Jul-2027	0%	11	0	11	1487

	Publication of Application Results (Weight=15%)	[Prof. Hanson, N. Camacho]	01-Jul-2027	120	15-Dec-2027	0%	120	0	120	1640
	Submit publication in American Journal of Physics
	Correspond with editors/referees	[Prof. Hanson]	01-Jul-2027	88	01-Nov-2027	0%	88	0	88	1596
	Copy editing, pay journal fees	[Prof. Hanson, N. Camacho]	01-Nov-2027	33	15-Dec-2027	0%	33	0	33	1640

	Assessment of Course Integrations (Weight=20%)	[Phys. Dept., ICS Dept.]	01-Jul-2027	38	23-Aug-2027	0%	38	0	38	1526
	Physics courses
	Obtain instructor feedback	[Phys. Dept.]	01-Jul-2027	11	15-Jul-2027	0%	11	0	11	1487
	Develop plans for future courses	[Phys. Dept.]	15-Jul-2027	12	01-Aug-2027	0%	12	0	12	1504
	Computer science courses
	Obtain instructor feedback	[ICS Dept., Prof. Hanson]	01-Aug-2027	10	15-Aug-2027	0%	10	0	10	1518
	Develop plans for future courses	[ICS Dept., Prof. Hanson]	15-Aug-2027	13	01-Sep-2027	0%	13	0	13	1535

	Additive Manufacturing, Semesters 7,8 (Weight=20%)	[Prof. Hanson, Undergraduates 3,6]	23-Sep-2027	168	15-May-2028	0%	168	0	168	1792
	Drone integration with solar charging and TX/RX
	Train new drone researcher	[Undergraduate 3]	23-Sep-2027	7	01-Oct-2027	0%	7	0	7	1565
	Learn to operate the drone	[Undergraduate 6]	01-Oct-2027	11	15-Oct-2027	0%	11	0	11	1579
	Solar charging integration	[Undergraduate 6]	15-Oct-2027	66	15-Jan-2028	0%	66	0	66	1671
	TX/RX integration with CReSIS collaboration	[Prof. Hanson, Undergraduates 3,6]	15-Jan-2028	65	15-Apr-2028	0%	65	0	65	1762
	Field testing
	Campus flight tests	[Undergraduates 3,6]	15-Jan-2028	22	15-Feb-2028	0%	22	0	22	1702
	TX/RX testing	[Prof. Hanson]	15-Jan-2028	22	15-Feb-2028	0%	22	0	22	1702
	Remote field test site selection	[Prof. Hanson]	15-Jan-2028	22	15-Feb-2028	0%	22	0	22	1702
	Final field tests	[Prof. Hanson, Undergraduates 3,6]	15-Feb-2028	65	15-May-2028	0%	65	0	65	1792

	Primary CEM Research, Semesters 7,8 (Weight=20%)	[Prof. Hanson]	23-Sep-2027	168	15-May-2028	0%	168	0	168	1792
	Integration of CEM and NuRadioMC via MEEP
	Creating kanban taskflow	[Prof. Hanson]	23-Aug-2027	8	01-Sep-2027	0%	8	0	8	1535
	Install updated version of NuRadioMC	[Prof. Hanson]	01-Sep-2027	11	15-Sep-2027	0%	11	0	11	1549
	Incorporate CEM designs into NuRadioMC detector	[Prof. Hanson]	15-Sep-2027	66	15-Dec-2027	0%	66	0	66	1640
	CEM Research with NuRadioMC
	Replacing ray-tracing with 3D propagation	[Prof. Hanson]	15-Dec-2027	109	15-May-2028	0%	109	0	109	1792
	Analytical Askaryan model as MEEP source, 3D prop.	[Prof. Hanson]	15-Dec-2027	109	15-May-2028	0%	109	0	109	1792

	Simulation and Software, Summer 2028 (Weight=20%)	[Prof. Hanson, Undergraduates 7,8]	15-May-2028	73	23-Aug-2028	0%	73	0	73	1892
	Event Reconstruction, IceCube Gen2
	Review analytic Askaryan model in NuRadioMC	[Prof. Hanson]	15-May-2028	14	01-Jun-2028	0%	14	0	14	1809
	Angular reconstruction	[Prof. Hanson, Undergraduate 7]	01-Jun-2028	32	15-Jul-2028	0%	32	0	32	1853
	Energy reconstruction	[Prof. Hanson, Undergraduate 8]	01-Jun-2028	32	15-Jul-2028	0%	32	0	32	1853
	Adding the Horizontal Polarization
	Evaluate improvements to reconstructions using Hpol	[Prof. Hanson, Undergraduates 7,8]	15-Jul-2028	28	23-Aug-2028	0%	28	0	28	1892

## Sheet5
	[Open-Source CEM and Additive Manufacturing, Year 5]				0%
	[Whittier College]
	[Profs. J. Hanson, F. Park, S. Zorba, S. Lagan, G. Piner]		Monday, June 19, 2023
	[Nayeli Camacho, Shaun Dunnick]

WBS	Task Names	Responsible Colleagues	Start	Net Work Days	Finish	% Complete	Net Work Days	Days Completed	Days Remaining	Days to Deadline		Jul 2028	Aug 2028	Sept 2028	Oct 2028	Nov 2028	Dec 2028	Jan 2029	Feb 2029	Mar 2029	Apr 2029	May 2029	Jun 2029	Jul 2029	Aug 2029
			01-Jul-2028	299	23-Aug-2029	0%	299	0	299	2257
	Backlog assessment (Weight=10%)	[Prof. Hanson]	01-Jul-2028	299	23-Aug-2029	0%	299	0	299	2257
	Assessment of Additive Manufacturing Goals
	RF antenna printed and tested	[Prof. Hanson]	01-Jul-2028	5	08-Jul-2028	0%	5	0	5	1846
	Phased array, Hpol array integrated and tested	[Prof. Hanson]	01-Jul-2028	5	08-Jul-2028	0%	5	0	5	1846
	Assessment of CEM Goals
	Phased array designs achieved	[Prof. Hanson]	01-Jul-2028	5	08-Jul-2028	0%	5	0	5	1846
	Machine learning progress	[Prof. Hanson]	01-Jul-2028	5	08-Jul-2028	0%	5	0	5	1846
	Assessment of Application Development
	Application coded and installed	[Prof. Hanson]	01-Jul-2028	5	08-Jul-2028	0%	5	0	5	1846
	Data collected	[Prof. Hanson]	01-Jul-2028	5	08-Jul-2028	0%	5	0	5	1846

	Simulation and Software, Semesters 9,10 (Weight=15%)	[Prof. Hanson, Undergraduates 7,8]	23-Aug-2028	190	15-May-2029	0%	190	0	190	2157
	Event Reconstruction, IceCube Gen2
	Review analytic Askaryan model in NuRadioMC	[Prof. Hanson]	23-Aug-2028	8	01-Sep-2028	0%	8	0	8	1901
	Angular reconstruction	[Undergraduate 7]	01-Sep-2028	76	15-Dec-2028	0%	76	0	76	2006
	Energy reconstruction	[Undergraduate 8]	01-Sep-2028	76	15-Dec-2028	0%	76	0	76	2006
	Adding the Horizontal Polarization
	Evaluate improvements to reconstructions using Hpol	[Prof. Hanson, Undergraduates 7,8]	15-Jan-2029	87	15-May-2029	0%	87	0	87	2157

	Application Development, Semesters 9,10 (Weight=15%)	[Phys. Dept., Undergraduates 9,10]	01-Sep-2028	255	23-Aug-2029	0%	255	0	255	2257
	Continuation of Course Implementation
	Train new students	[Prof. Hanson, Undergraduates 9,10]	01-Sep-2028	11	15-Sep-2028	0%	11	0	11	1915
	Collect new data sets	[Undergraduates 9,10]	01-Sep-2028	76	15-Dec-2028	0%	76	0	76	2006
	Gather student feedback	[Prof. Hanson]	10-Dec-2028	5	15-Dec-2028	0%	5	0	5	2006
	Refining Application
	Refining machine learning algorithm	[Undergraduate 9]	15-Jan-2029	87	15-May-2029	0%	87	0	87	2157
	Refining visual elements	[Undergraduate 10]	15-Jan-2029	87	15-May-2029	0%	87	0	87	2157
	Report to Wider Faculty on Publication, Progress
	Colloquium to STEM faculty	[Prof. Hanson]	01-Jan-2029	24	01-Feb-2029	0%	24	0	24	2054
	OER talk in Wardman Collaboratory	[Prof. Hanson]	01-Feb-2029	21	01-Mar-2029	0%	21	0	21	2082
	Implementation in New Courses
	Explore course options	[Phys. Dept., ICS Dept.]	01-Mar-2029	22	01-Apr-2029	0%	22	0	22	2113
	Collaborate with other professors	[Phys. Dept., ICS Dept.]	01-Mar-2029	22	01-Apr-2029	0%	22	0	22	2113

	Backlog Fulfillment, Semesters 9,10 (Weight=60%)	[Prof. Hanson, Undergraduates 9,10]	23-Aug-2028	190	15-May-2029	0%	190	0	190	2157
	Additive Manufacturing
	Complete old assignments	[Prof. Hanson, Undergraduates 9,10]	23-Aug-2028	190	15-May-2029	0%	190	0	190	2157
	CEM and MEEP
	Complete old assignments	[Prof. Hanson, Undergraduates 9,10]	23-Aug-2028	190	15-May-2029	0%	190	0	190	2157
	Application Development
	Complete old assignments	[Prof. Hanson, Undergraduates 9,10]	23-Aug-2028	190	15-May-2029	0%	190	0	190	2157