## Gantt Chart
	[Open-Source CEM and Additive Manufacturing, Year 2]				5%
	[Whittier College]
	[Profs. J. Hanson, F. Park, S. Zorba, S. Lagan, G. Piner]		Tuesday, June 13, 2023
	[Nayeli Camacho, Shaun Dunnick]

WBS	Task Names	Responsible Colleagues	Start	Net Work Days	Finish	% Complete	Calendar days	Days Completed	Days Remaining		Jul 2025	Aug 2025	Sept 2025	Oct 2026	Nov 2025	Dec 2025	Jan 2026	Feb 2026	Mar 2026	Apr 2026	May 2026	Jun 2026	Jul 2026	Aug 2026
			23-Aug-2025	260	23-Aug-2026	5%	366	13	353
	Recruitment (Weight=5%)	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	100%	32	66	-34
	Standard undergraduate recruitment procedure
	Undergraduate STEM researchers	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	100%	32	22	10
	Undergraduate app/code designers	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	100%	32	22	10
	Undergraduate Spanish translator	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	100%	32	22	10

	Primary CEM Research, Semester 3 (Weight=15%)	[Prof. Hanson, Undergraduates 1,2]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	CEM Application to UHE Neutrino Research
	Explore horizontal array polarization in ice	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Polarization response calculation	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	S-Parameters analysis	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Inclusion of coaxial cable in simulation	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Embed in realistic ice profile	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Machine Learning Optimization
	Search for horizontal polarization optimization	[Prof. Hanson, Undergraduate 2]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Adjusting genetic programming style	[Prof. Hanson, Undergraduate 2]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Testing new algorithms	[Prof. Hanson, Undergraduate 2]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115

	Additive Manufacturing, Semester 3 (Weight=15%)	[S. Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Printing with Electrifi Filament
	Continue print progress from Summer 2025	[S. Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Modify designs to accommodate Hpol results	[S. Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Begin array integration	[S. Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	RF bench testing of prototype array	[S. Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115

	Application Development., Semesters 3,4 (Weight=20%)	[Prof. Hanson, Undergraduate 4]	23-Aug-2025	190	15-May-2026	0%	266	0	266
	Creating Project Plan with Students
	Update Kanban taskflow	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	0%	32	0	32
	Implementation of STEM content in Android SDK	[Undergraduate 4]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Designing Visual Environment
	Integrating visual content on Android app	[Undergraduate 4]	15-Jan-2026	87	15-May-2026	0%	121	0	121
	Experimenting with machine learning integration	[Undergraduate 4]	15-Jan-2026	87	15-May-2026	0%	121	0	121

	Publication in Electronics, Semester 4 (Weight=25%)	[Prof. Hanson, Undergraduates 1,2,3, N. Camacho]	15-Jan-2026	157	23-Aug-2026	0%	221	0	221
	Compiling results, writing the article
	Creating outline, writing text, gathering references	[Prof. Hanson]	15-Jan-2026	87	15-May-2026	0%	121	0	121
	Gathering results and polishing figures	[Undergraduates 1,2,3]	15-Jan-2026	87	15-May-2026	0%	121	0	121
	Publishing
	Corresponding with referees and editor	[Prof. Hanson]	15-May-2026	71	23-Aug-2026	0%	101	0	101
	Paying associated fees	[M. Camacho]	15-May-2026	71	23-Aug-2026	0%	101	0	101

	CEM/3D Print Summer Research 2026 (Weight=20%)	[Prof. Hanson, S. Dunnick, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	101	0	101
	Finish backlog of prior work
	Publication, HPol analysis, machine learning optimizations	[Prof. Hanson, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	101	0	101
	Prototype testing
	Practicing design loop: CEM to print	[Prof. Hanson, S. Dunnick, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	101	0	101
	Integration of prototype array	[Prof. Hanson, S. Dunnick, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	101	0	101
	Archiving progress
	Creating official, public code repository	[Prof. Hanson, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	101	0	101
	CAD design storage	[Prof. Hanson, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	101	0	101