## Gantt Chart
	[Open-Source CEM and Additive Manufacturing]				50%
	[Whittier College]
	[Prof. Jordan Hanson, Prof. Fred Park, Nayeli Camacho]		Monday, June 5, 2023

WBS	Task Names	Responsible Colleagues	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Project Start
			07/01/2024	1304	07/01/2029	50%	1827			07/01/2024	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28
	Hardware Acquisition	[Prof. Hanson, N. Camacho, F. Park]	07/01/2024	24	08/01/2024	50%	32	10	10
	3D Printer Acquisition
	Obtain quotes	[J. Hanson]	01-Jul-2024	6	08-Jul-2024	50%	8	3	3
	Complete purchase	[N. Camacho]	10-Jul-2024	4	15-Jul-2024	50%	6	2	2
	3D Printer Filament Acquisition
	Obtain quotes	[J. Hanson]	01-Jul-2024	6	08-Jul-2024	50%	8	3	3
	Complete purchase	[N. Camacho]	10-Jul-2024	4	15-Jul-2024	50%	6	2	2
	GPU/Multicore Server
	Perform market comparison	[F. Park]	01-Jul-2024	24	01-Aug-2024	50%	32	12	12
	Obtain quotes	[J. Hanson]	01-Aug-2024	10	14-Aug-2024	50%	14	5	5
	Complete purchase	[N. Camacho]	14-Aug-2024	2	15-Aug-2024	50%	2	1	1

	Recruitment	[Prof. Hanson]	08/23/2024	22	09/23/2024	50%	32	11	11
	Undergraduate STEM researchers
	Standard recruitment procedure	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	50%	32	11	11
	Undergraduate App Code/Design
	Standard recruitment procedure	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	50%	32	11	11
	Translator Recruitment
	Standard recruitment procedure	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	50%	32	11	11

	Run Published CEM Codes	[Prof. Hanson, Undergraduates 1,2]	09/23/2024	6	30-Sep-2024	50%	8	6	6
	Initial CEM Training, Linux Accts.
	CEM Training	[Prof. Hanson, Undergraduates 1,2]	23-Sep-2024	6	30-Sep-2024	50%	8	3	3
	Account creation	[Prof. Hanson]	23-Sep-2024	6	30-Sep-2024	50%	8	3	3
	Updating CEM Code
	Unpack and test original code	[Prof. Hanson]	25-Sep-2024	6	02-Oct-2024	52%	8	3	3

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		1/1/24
		4/20/24
		12/25/24