## Gantt Chart
	[Open-Source CEM and Additive Manufacturing, Year 1]				0%
	[Whittier College]
	[Profs. J. Hanson, F. Park, S. Zorba, S. Lagan, G. Piner]		Tuesday, June 6, 2023
	[Nayeli Camacho, Shaun Dunnick]

WBS	Task Names	Responsible Colleagues	Start	Net Work Days	Finish	% Complete	Calendar days	Days Completed	Days Remaining
			01-Jul-2024	300	23-Aug-2025	0%	419	0	419
	Hardware Acquisition (Weight=10%)	[Prof. Hanson, N. Camacho, F. Park]	07-Jan-2024	149	01-Aug-2024	0%	208	0	208
	3D Printer Acquisition
	Obtain quotes	[Prof. Hanson]	01-Jul-2024	6	08-Jul-2024	0%	8	0	8
	Complete purchase	[N. Camacho]	10-Jul-2024	4	15-Jul-2024	0%	6	0	6
	3D Printer Filament Acquisition
	Obtain quotes	[Prof. Hanson]	01-Jul-2024	6	08-Jul-2024	0%	8	0	8
	Complete purchase	[N. Camacho]	10-Jul-2024	4	15-Jul-2024	0%	6	0	6
	GPU/Multicore Server
	Perform market comparison	[F. Park]	01-Jul-2024	24	01-Aug-2024	0%	32	0	32
	Obtain quotes	[Prof. Hanson]	01-Aug-2024	10	14-Aug-2024	0%	14	0	14
	Complete purchase	[N. Camacho]	14-Aug-2024	2	15-Aug-2024	0%	2	0	2
	RF Lab Hardware
	RF cables and connectors	[Prof. Hanson]	01-Jul-2024	24	01-Aug-2024	0%	32	0	32

	Recruitment (Weight=5%)	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	0%	32	0	32
	Undergraduate STEM researchers
	Standard recruitment procedure	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	0%	32	0	32
	Undergraduate App Code/Design
	Standard recruitment procedure	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	0%	32	0	32

	Run Published CEM Codes (Weight=5%)	[Prof. Hanson, Undergraduates 1,2]	23-Sep-2024	6	30-Sep-2024	0%	8	0	8
	Initial CEM Training, Linux Accts.
	CEM Training	[Prof. Hanson, Undergraduates 1,2]	23-Sep-2024	6	30-Sep-2024	0%	8	0	8
	Account creation	[Prof. Hanson]	23-Sep-2024	6	30-Sep-2024	0%	8	0	8
	Updating CEM Code
	Unpack and test original code	[Prof. Hanson]	25-Sep-2024	6	02-Oct-2024	0%	8	0	8

	Course Integrations (Weight=10%)	[Profs. Hanson, Lagan, Zorba, Piner, and Park]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Physics Courses
	Algebra-Based Physics II	[Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Calculus-Based Physics II	[Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Optics	[Profs. Zorba and Hanson]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Electromagnetic Theory	[Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Computational Physics	[Profs. Lagan and Hanson]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Computer Science Courses
	Computer Logic and Digital Circuit Design	[Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Digital Signal Processing	[Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Introduction to Data Science with Python	[Profs. Hanson and Piner]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Machine Learning	[Profs. Hanson and Park]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54

	Primary CEM Research, Semesters 1 and 2 (Weight=10%)	[Prof. Hanson, Undergraduates 1,2]	23-Aug-2024	190	15-May-2025	0%	266	0	266
	CEM Simulations, Data Visualization
	3D visualization of RF horn design	[Prof. Hanson, Undergraduate 1]	23-Sep-2024	60	15-Dec-2024	0%	84	0	84
	Time-domain computations, phase analysis	[Prof. Hanson, Undergraduate 1]	23-Sep-2024	60	15-Dec-2024	0%	84	0	84
	S-Parameters analysis	[Prof. Hanson, Undergraduate 1]	23-Sep-2024	60	15-Dec-2024	0%	84	0	84
	Inclusion of coaxial cable in simulation	[Prof. Hanson, Undergraduate 1]	23-Sep-2024	60	15-Dec-2024	0%	84	0	84
	Embed in various media	[Prof. Hanson, Undergraduate 1]	23-Sep-2024	60	15-Dec-2024	0%	84	0	84
	Machine Learning Optimization
	Background research for algorithms	[Prof. Hanson, Undergraduate 2]	23-Sep-2024	169	15-May-2025	0%	235	0	235
	Learning genetic programming styles	[Prof. Hanson, Undergraduate 2]	23-Sep-2024	169	15-May-2025	0%	235	0	235
	CEM implementation with basic RF horn	[Prof. Hanson, Undergraduate 2]	23-Sep-2024	169	15-May-2025	0%	235	0	235
	RF antenna optimization	[Prof. Hanson, Undergraduate 2]	23-Sep-2024	169	15-May-2025	0%	235	0	235

	Additive Manufacturing, Semesters 1 and 2 (Weight=10%)	[Shaun Dunnick, Undergraduates 1,3]	23-Aug-2024	190	15-May-2025	0%	266	0	266
	Printing with PLA Filament
	Updating prior designs	[Shaun Dunnick, Undergraduates 1,3]	23-Sep-2024	60	15-Dec-2024	0%	84	0	84
	Practice file format conversion	[Shaun Dunnick, Undergraduates 1,3]	23-Sep-2024	60	15-Dec-2024	0%	84	0	84
	Print test object	[Shaun Dunnick, Undergraduates 1,3]	23-Sep-2024	60	15-Dec-2024	0%	84	0	84
	Print PLA antenna model	[Shaun Dunnick, Undergraduates 1,3]	23-Sep-2024	60	15-Dec-2024	0%	84	0	84
	Printing with Electrifi Filament
	Print test object	[Shaun Dunnick, Undergraduates 1,3]	15-Jan-2025	87	15-May-2025	0%	121	0	121
	Perform resistivity measurements	[Shaun Dunnick, Undergraduates 1,3]	15-Jan-2025	87	15-May-2025	0%	121	0	121
	Print simple antenna	[Shaun Dunnick, Undergraduates 1,3]	15-Jan-2025	87	15-May-2025	0%	121	0	121
	Print complex antenna	[Shaun Dunnick, Undergraduates 1,3]	15-Jan-2025	87	15-May-2025	0%	121	0	121

	Application Development, Semesters 1 and 2 (Weight=10%)	[Prof. Hanson, Undergraduate 4]	23-Aug-2024	190	15-May-2025	0%	266	0	266
	Creating Project Plan with Students
	Creating kanban taskflow	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	0%	32	0	32
	Experimenting with Android SDK	[Undergraduate 4]	23-Aug-2024	81	15-Dec-2024	0%	115	0	115
	Updating prior code	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	0%	32	0	32
	Designing Visual Environment
	Updating prior designs	[Undergraduate 4]	23-Aug-2024	81	15-Dec-2024	0%	115	0	115
	Displaying content on Android app	[Undergraduate 4]	15-Jan-2025	87	15-May-2025	0%	121	0	121

	Primary CEM Research, Summer 2025 (Weight=20%)	[Prof. Hanson, Undergraduates 1,2]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	CEM Simulations, Data Visualization
	Time-domain computations, phase analysis	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	S-Parameters analysis	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Inclusion of coaxial cable in simulation	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Embed in various media	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Machine Learning Optimization
	3D visualization of optimized antenna	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Explore array optimizations in ice, Hpol	[Prof. Hanson, Undergraduate 2]	15-May-2025	72	23-Aug-2025	0%	101	0	101

	Additive Manufacturing, Summer 2025 (Weight=20%)	[Shaun Dunnick, Undergraduates 1,3]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Printing with Electrifi Filament
	Updating prior designs	[Shaun Dunnick, Undergraduates 1,3]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Continue printing complex antenna	[Shaun Dunnick, Undergraduates 1,3]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Real S-parameter measurement	[Prof. Hanson, Undergraduates 1,3]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Real radiation pattern measurement	[Prof. Hanson, Undergraduates 1,3]	15-May-2025	72	23-Aug-2025	0%	101	0	101

## Sheet2
	[Open-Source CEM and Additive Manufacturing, Year 2]				#REF!
	[Whittier College]
	[Profs. J. Hanson, F. Park, S. Zorba, S. Lagan, G. Piner]		Tuesday, June 6, 2023
	[Nayeli Camacho, Shaun Dunnick]

WBS	Task Names	Responsible Colleagues	Start	Net Work Days	Finish	% Complete	Calendar days	Days Completed	Days Remaining
			23-Aug-2025	260	23-Aug-2026	#REF!	366	#REF!	#REF!
	Recruitment (Weight=5%)	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	0%	32	0	32
	Undergraduate STEM researchers
	Standard recruitment procedure	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	0%	32	0	32
	Undergraduate App Code/Design
	Standard recruitment procedure	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	0%	32	0	32
	Translator Recruitment
	Standard recruitment procedure	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	0%	32	0	32

	Primary CEM Research, Semester 3 (Weight=10%)	[Prof. Hanson, Undergraduates 1,2]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	CEM Application to UHE Neutrino Research
	Explore horizontal array polarization in ice	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Polarization response calculation	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	S-Parameters analysis	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Inclusion of coaxial cable in simulation	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Embed in realistic ice profile	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Machine Learning Optimization
	Search for horizontal polarization optimization	[Prof. Hanson, Undergraduate 2]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Adjusting genetic programming style	[Prof. Hanson, Undergraduate 2]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Testing new algorithms	[Prof. Hanson, Undergraduate 2]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115

	Additive Manufacturing, Semester 3 (Weight=10%)	[Shaun Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	0%	115	#REF!	#REF!
	Printing with Electrifi Filament
	Continue print progress from Summer 2025	[Shaun Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Modify designs to accommodate Hpol results	[Shaun Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	Begin array integration	[Shaun Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	RF bench testing of prototype array	[Shaun Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115

	Application Development, Semesters 3 and 4 (Weight=10%)	[Prof. Hanson, Undergraduate 4]	23-Aug-2024	190	15-May-2025	0%	266	0	266
	Creating Project Plan with Students
	Creating Kanban Taskflow	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	0%	32	0	32
	Experimenting with Android SDK	[Undergraduate 4]	23-Aug-2024	81	15-Dec-2024	0%	115	0	115
	Updating Prior Code	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	0%	32	0	32
	Designing Visual Environment
	Updating Prior Designs	[Undergraduate 4]	23-Aug-2024	81	15-Dec-2024	0%	115	0	115
	Displaying Content on Android App	[Undergraduate 4]	15-Jan-2025	87	15-May-2025	0%	121	0	121

	Primary CEM Research, Summer 2025 (Weight=20%)	[Prof. Hanson, Undergraduates 1,2]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	CEM Simulations, Data Visualization
	Time-domain computations, phase analysis	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	S-Parameters analysis	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Inclusion of coaxial cable in simulation	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Embed in various media	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Machine Learning Optimization
	3D Visualization of Optimized Antenna	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Explore Array Optimizations in Ice, Hpol	[Prof. Hanson, Undergraduate 2]	15-May-2025	72	23-Aug-2025	0%	101	0	101

	Additive Manufacturing, Summer 2025 (Weight=20%)	[Shaun Dunnick, Undergraduates 1,3]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Printing with Electrifi Filament
	Updating Prior Designs	[Shaun Dunnick, Undergraduates 1,3]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Continue Printing Complex Antenna	[Shaun Dunnick, Undergraduates 1,3]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Real S-Parameter Measurement	[Prof. Hanson, Undergraduates 1,3]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Real Radiation Pattern Measurement	[Prof. Hanson, Undergraduates 1,3]	15-May-2025	72	23-Aug-2025	0%	101	0	101