## Gantt Chart
	[Open-Source CEM and Additive Manufacturing, Year 1]				39%
	[Whittier College]
	[Profs. J. Hanson, F. Park, S. Zorba, S. Lagan, G. Piner]		Monday, June 12, 2023
	[Nayeli Camacho, Shaun Dunnick]

WBS	Task Names	Responsible Colleagues	Start	Net Work Days	Finish	% Complete	Calendar days	Days Completed	Days Remaining		Jul 2024	Aug 2024	Sept 2024	Oct 2024	Nov 2024	Dec 2024	Jan 2025	Feb 2025	Mar 2025	Apr 2025	May 2025	Jun 2025	Jul 2025	Aug 2025
			01-Jul-2024	300	23-Aug-2025	39%	419	118	301
	Hardware Acquisition (Weight=10%)	[Prof. Hanson, N. Camacho, F. Park]	07-Jan-2024	149	01-Aug-2024	100%	208	56	152
	3D Printer Acquisition
	Obtain quotes	[Prof. Hanson]	01-Jul-2024	6	08-Jul-2024	100%	8	6	2
	Complete purchase	[N. Camacho]	10-Jul-2024	4	15-Jul-2024	100%	6	4	2
	3D Printer Filament Acquisition
	Obtain quotes	[Prof. Hanson]	01-Jul-2024	6	08-Jul-2024	100%	8	6	2
	Complete purchase	[N. Camacho]	10-Jul-2024	4	15-Jul-2024	100%	6	4	2
	GPU/Multicore Server
	Perform market comparison	[F. Park]	01-Jul-2024	24	01-Aug-2024	100%	32	24	8
	Obtain quotes	[Prof. Hanson]	01-Aug-2024	10	14-Aug-2024	100%	14	10	4
	Complete purchase	[N. Camacho]	14-Aug-2024	2	15-Aug-2024	100%	2	2	0
	RF Lab Hardware
	RF cables and connectors	[Prof. Hanson]	01-Jul-2024	24	01-Aug-2024	100%	32	24	8

	Recruitment (Weight=5%)	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	100%	32	22	10
	Standard undergraduate recruitment procedure
	Undergraduate STEM researchers	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	100%	32	22	10
	Undergraduate app/code designers	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	100%	32	22	10

	Run Published CEM Codes (Weight=5%)	[Prof. Hanson, Undergraduates 1,2]	23-Sep-2024	6	30-Sep-2024	100%	8	12	-4
	Initial CEM Training, Linux Accts.
	CEM Training	[Prof. Hanson, Undergraduates 1,2]	23-Sep-2024	6	30-Sep-2024	100%	8	6	2
	Account creation	[Prof. Hanson]	23-Sep-2024	6	30-Sep-2024	100%	8	6	2
	Updating CEM Code
	Unpack and test original code	[Prof. Hanson]	25-Sep-2024	10	08-Oct-2024	100%	14	10	4

	Course Integrations (Weight=10%)	[Profs. Hanson, Lagan, Zorba, Piner, and Park]	01-Jul-2024	40	23-Aug-2024	44%	54	40	14
	Physics Courses
	Algebra-Based Physics II	[Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	100%	54	40	14
	Calculus-Based Physics II	[Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Optics	[Profs. Zorba and Hanson]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Electromagnetic Theory	[Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	100%	54	40	14
	Computational Physics	[Profs. Lagan and Hanson]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Computer Science Courses
	Computer Logic and Digital Circuit Design	[Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	100%	54	40	14
	Digital Signal Processing	[Prof. Hanson]	01-Jul-2024	40	23-Aug-2024	100%	54	40	14
	Introduction to Data Science with Python	[Profs. Hanson and Piner]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54
	Machine Learning	[Profs. Hanson and Park]	01-Jul-2024	40	23-Aug-2024	0%	54	0	54

	Primary CEM Research, Semesters 1 and 2 (Weight=10%)	[Prof. Hanson, Undergraduates 1,2]	23-Aug-2024	190	15-May-2025	68%	266	120	146
	CEM Simulations, Data Visualization
	3D visualization of RF horn design	[Prof. Hanson, Undergraduate 1]	23-Sep-2024	60	15-Dec-2024	100%	84	60	24
	Time-domain computations, phase analysis	[Prof. Hanson, Undergraduate 1]	23-Sep-2024	60	15-Dec-2024	100%	84	60	24
	S-Parameters analysis	[Prof. Hanson, Undergraduate 1]	23-Sep-2024	60	15-Dec-2024	100%	84	60	24
	Inclusion of coaxial cable in simulation	[Prof. Hanson, Undergraduate 1]	23-Sep-2024	60	15-Dec-2024	50%	84	30	54
	Embed in various media	[Prof. Hanson, Undergraduate 1]	23-Sep-2024	60	15-Dec-2024	50%	84	30	54
	Machine Learning Optimization
	Background research for algorithms	[Prof. Hanson, Undergraduate 2]	23-Sep-2024	169	15-May-2025	100%	235	169	66
	Learning genetic programming styles	[Prof. Hanson, Undergraduate 2]	23-Sep-2024	169	15-May-2025	100%	235	169	66
	CEM implementation with basic RF horn	[Prof. Hanson, Undergraduate 2]	23-Sep-2024	169	15-May-2025	50%	235	84	151
	RF antenna optimization	[Prof. Hanson, Undergraduate 2]	23-Sep-2024	169	15-May-2025	0%	235	0	235

	Additive Manufacturing, Semesters 1 and 2 (Weight=10%)	[S. Dunnick, Undergraduate 3]	23-Aug-2024	190	15-May-2025	33%	266	120	146
	Printing with PLA Filament
	Updating prior designs	[S. Dunnick, Undergraduate 3]	23-Sep-2024	60	15-Dec-2024	100%	84	60	24
	Practice file format conversion	[S. Dunnick, Undergraduate 3]	23-Sep-2024	60	15-Dec-2024	100%	84	60	24
	Print test object	[S. Dunnick, Undergraduate 3]	23-Sep-2024	60	15-Dec-2024	100%	84	60	24
	Print PLA antenna model	[S. Dunnick, Undergraduate 3]	23-Sep-2024	60	15-Dec-2024	25%	84	15	69
	Printing with Electrifi Filament
	Print test object	[S. Dunnick, Undergraduate 3]	15-Jan-2025	87	15-May-2025	0%	121	0	121
	Perform resistivity measurements	[S. Dunnick, Undergraduate 3]	15-Jan-2025	87	15-May-2025	0%	121	0	121
	Print simple antenna	[S. Dunnick, Undergraduate 3]	15-Jan-2025	87	15-May-2025	0%	121	0	121
	Print complex antenna	[S. Dunnick, Undergraduate 3]	15-Jan-2025	87	15-May-2025	0%	121	0	121

	Application Development, Semesters 1 and 2 (Weight=10%)	[Prof. Hanson, Undergraduate 4]	23-Aug-2024	190	15-May-2025	48%	266	141	125
	Creating Project Plan with Students
	Creating kanban taskflow	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	100%	32	22	10
	Experimenting with Android SDK	[Undergraduate 4]	23-Aug-2024	81	15-Dec-2024	100%	115	81	34
	Updating prior code	[Prof. Hanson]	23-Aug-2024	22	23-Sep-2024	100%	32	22	10
	Designing Visual Environment
	Updating prior designs	[Undergraduate 4]	23-Aug-2024	81	15-Dec-2024	10%	115	8	107
	Displaying content on Android app	[Undergraduate 4]	15-Jan-2025	87	15-May-2025	10%	121	8	113

	Primary CEM Research, Summer 2025 (Weight=20%)	[Prof. Hanson, Undergraduates 1,2]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	CEM Simulations, Data Visualization
	Time-domain computations, phase analysis	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	S-Parameters analysis	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Inclusion of coaxial cable in simulation	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Embed in various media	[Prof. Hanson, Undergraduate 1]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Machine Learning Optimization
	3D visualization of optimized antenna	[Prof. Hanson, Undergraduate 2]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Explore array optimizations in ice, Hpol	[Prof. Hanson, Undergraduate 2]	15-May-2025	72	23-Aug-2025	0%	101	0	101

	Additive Manufacturing, Summer 2025 (Weight=20%)	[S. Dunnick, Undergraduates 1,3]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Printing with Electrifi Filament
	Updating prior designs	[S. Dunnick, Undergraduate 3]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Continue printing complex antenna	[S. Dunnick, Undergraduate 3]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Real S-parameter measurement	[Prof. Hanson, Undergraduate 3]	15-May-2025	72	23-Aug-2025	0%	101	0	101
	Real radiation pattern measurement	[Prof. Hanson, Undergraduate 3]	15-May-2025	72	23-Aug-2025	0%	101	0	101

## Sheet2
	[Open-Source CEM and Additive Manufacturing, Year 2]				27%
	[Whittier College]
	[Profs. J. Hanson, F. Park, S. Zorba, S. Lagan, G. Piner]		Monday, June 12, 2023
	[Nayeli Camacho, Shaun Dunnick]

WBS	Task Names	Responsible Colleagues	Start	Net Work Days	Finish	% Complete	Calendar days	Days Completed	Days Remaining		Jul 2025	Aug 2025	Sept 2025	Oct 2026	Nov 2025	Dec 2025	Jan 2026	Feb 2026	Mar 2026	Apr 2026	May 2026	Jun 2026	Jul 2026	Aug 2026
			23-Aug-2025	260	23-Aug-2026	27%	366	71	295
	Recruitment (Weight=5%)	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	100%	32	66	-34
	Standard undergraduate recruitment procedure
	Undergraduate STEM researchers	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	100%	32	22	10
	Undergraduate app/code designers	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	100%	32	22	10
	Undergraduate Spanish translator	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	100%	32	22	10

	Primary CEM Research, Semester 3 (Weight=15%)	[Prof. Hanson, Undergraduates 1,2]	23-Aug-2025	81	15-Dec-2025	64%	115	416	-301
	CEM Application to UHE Neutrino Research
	Explore horizontal array polarization in ice	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	100%	115	81	34
	Polarization response calculation	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	100%	115	81	34
	S-Parameters analysis	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	100%	115	81	34
	Inclusion of coaxial cable in simulation	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	50%	115	40	75
	Embed in realistic ice profile	[Prof. Hanson, Undergraduate 1]	23-Aug-2025	81	15-Dec-2025	10%	115	8	107
	Machine Learning Optimization
	Search for horizontal polarization optimization	[Prof. Hanson, Undergraduate 2]	23-Aug-2025	81	15-Dec-2025	100%	115	81	34
	Adjusting genetic programming style	[Prof. Hanson, Undergraduate 2]	23-Aug-2025	81	15-Dec-2025	50%	115	40	75
	Testing new algorithms	[Prof. Hanson, Undergraduate 2]	23-Aug-2025	81	15-Dec-2025	5%	115	4	111

	Additive Manufacturing, Semester 3 (Weight=15%)	[S. Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	13%	115	40	75
	Printing with Electrifi Filament
	Continue print progress from Summer 2025	[S. Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	25%	115	20	95
	Modify designs to accommodate Hpol results	[S. Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	25%	115	20	95
	Begin array integration	[S. Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115
	RF bench testing of prototype array	[S. Dunnick, Undergraduate 3]	23-Aug-2025	81	15-Dec-2025	0%	115	0	115

	Application Development., Semesters 3,4 (Weight=20%)	[Prof. Hanson, Undergraduate 4]	23-Aug-2025	190	15-May-2026	54%	266	150	116
	Creating Project Plan with Students
	Update Kanban taskflow	[Prof. Hanson]	23-Aug-2025	22	23-Sep-2025	100%	32	22	10
	Implementation of STEM content in Android SDK	[Undergraduate 4]	23-Aug-2025	81	15-Dec-2025	100%	115	81	34
	Designing Visual Environment
	Integrating visual content on Android app	[Undergraduate 4]	15-Jan-2026	87	15-May-2026	50%	121	43	78
	Experimenting with machine learning integration	[Undergraduate 4]	15-Jan-2025	87	15-May-2025	5%	121	4	117

	Publication in Electronics, Semester 4 (Weight=25%)	[Prof. Hanson, Undergraduates 1,2,3, N. Camacho]	15-Jan-2026	157	23-Aug-2026	0%	221	0	221
	Compiling results, writing the article
	Creating outline, writing text, gathering references	[Prof. Hanson]	15-Jan-2026	87	15-May-2026	0%	121	0	121
	Gathering results and polishing figures	[Undergraduates 1,2,3]	15-Jan-2026	87	15-May-2026	0%	121	0	121
	Publishing
	Corresponding with referees and editor	[Prof. Hanson]	15-May-2026	71	23-Aug-2026	0%	101	0	101
	Paying associated fees	[M. Camacho]	15-May-2026	71	23-Aug-2026	0%	101	0	101

	CEM/3D Print Summer Research 2026 (Weight=20%)	[Prof. Hanson, S. Dunnick, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	101	0	101
	Finish backlog of prior work
	Publication, HPol analysis, machine learning optimizations	[Prof. Hanson, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	101	0	101
	Prototype testing
	Practicing design loop: CEM to print	[Prof. Hanson, S. Dunnick, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	101	0	101
	Integration of prototype array	[Prof. Hanson, S. Dunnick, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	101	0	101
	Archiving progress
	Creating official, public code repository	[Prof. Hanson, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	101	0	101
	CAD design storage	[Prof. Hanson, Undergraduate 1]	15-May-2026	71	23-Aug-2026	0%	101	0	101